## Summary & Timeline
Need a helping hand with your strategy? We got you.
First Date of Sale/Promotion: | 2024-11-25 | << UPDATE THIS DATE FIRST
MAKE A COPY | SUMMARY of GOAL / FINDINGS | DUE DATE
🌎 UNIVERSAL 🌎
Review Previous Year Holiday Sale Performance |  | 2024-08-05
Research Competitor & Market Trends |  | 2024-08-05
Define Core Audience (Interests, Demographics & Geography) |  | 2024-08-05
Define Advertising Budget (Update Budget Sheet) |  | 2024-08-05
Optimize GA4 & GTM Configurations |  | 2024-08-08
Define Uniform Design Elements |  | 2024-09-01
Create Optimized Promo Codes |  | 2024-08-16
Set Code Freeze Dates |  | 2024-09-16
Review Promotion Performance & Analyze For 2025 |  | 2025-03-05
📈 SEO / CRO 📈
Test & Resolve Site Speed Errors |  | 2024-07-28
Test & Resolve Mobile Usability Errors |  | 2024-07-28
Define Strategy & KPIs for Organic Performance |  | 2024-08-16
Publish Preview Blog |  | 2024-09-21
Publish Second Variant Preview Blog |  | 2024-10-26
Develop A/B Test Landing Page Content |  | 2024-09-26
Test Promo Codes |  | 2024-10-26
🔎 GOOGLE ADS 🔎
Define Strategy & KPIs for Google Ads |  | 2024-08-16
Create GA4 & Google Ads Audiences |  | 2024-09-21
Draft Promo Campaigns for A/B Testing (min. 2 per promo code) |  | 2024-09-16
Enable Campaigns w/ preview text |  | 2024-11-15
Update Campaigns w/ live promo text |  | 2024-11-24
📬 EMAIL MARKETING 📬
Define Strategy & KPIs for Email |  | 2024-08-16
Segment Audiences |  | 2024-09-06
Create Interest Gauge Email |  | 2024-09-06
Create Preview Email |  | 2024-09-09
Create Reminder Preview Email |  | 2024-09-09
Send Final Reminder Preview Email |  | 2024-09-10
Create Subscribers Only 24-hour |  | 2024-09-10
Create Promo Kickoff Email |  | 2024-09-11
Create Promo Reminder Email |  | 2024-09-11
Create Promo Ending (48 hours) Email |  | 2024-09-12
Create Promo Ending (24 hours) Email |  | 2024-09-12
Create Interest Gauge Email |  | 2024-10-11
Send Preview Email |  | 2024-10-26
Send Reminder Preview Email |  | 2024-11-11
Send Final Reminder Preview Email |  | 2024-11-18
Send Subscribers Only 24-hour |  | 2024-11-24
Send Promo Kickoff Email |  | 2024-11-25
Send Promo Reminder Email |  | 2024-11-28
Send Reminder emails every 2 days until 48 hours before promo end |  | N/A
Send Promo Ending (48 hours) Email |  | 48 Hours before promo end date
Send Promo Ending (24 hours) Email |  | 24 Hours before promo end date
💬 SMS MARKETING 💬
Define Strategy & KPIs for SMS |  | 2024-08-16
Segment Audiences |  | 2024-09-06
Create Preview SMS |  | 2024-09-09
Create Reminder Preview SMS |  | 2024-09-09
Send Final Reminder Preview SMS |  | 2024-09-10
Create Subscribers Only 24-hour |  | 2024-09-10
Create Promo Kickoff SMS |  | 2024-09-11
Create Promo Reminder SMS |  | 2024-09-11
Create Promo Ending (48 hours) SMS |  | 2024-09-12
Create Promo Ending (24 hours) SMS |  | 2024-09-12
Send Preview SMS |  | 2024-10-26
Send Reminder Preview SMS |  | 2024-11-11
Send Final Reminder Preview SMS |  | 2024-11-18
Send Subscribers Only 24-hour |  | 2024-11-24
Send Promo Kickoff SMS |  | 2024-11-25
Send Promo Reminder SMS |  | 2024-11-28
Send Reminder SMSs every 2 days until 48 hours before promo end |  | N/A
Send Promo Ending (48 hours) SMS |  | 48 Hours before promo end date
Send Promo Ending (24 hours) SMS |  | 24 Hours before promo end date
🎙 AUDIO ADVERTISING (RADIO/PODCAST) 🎙
Define Strategy & KPIs for Radio/Podcast |  | 2024-08-16
Define Opportunities Shortlist w/ market research findings |  | 2024-08-23
Contact Podcasts/Stations & Review Rates |  | 2024-08-23
Select Podcast(s) / Station(s) |  | 2024-09-09
Understand Options (Host-Read, etc.) & Curate Content / UTM Parameters |  | 2024-10-09
Content Submission Dependent Upon Podcast/Radio Policy |  | TBD
🤝 PARTNER/REFERRAL MARKETING 🤝
Define Strategy & KPIs for Referring Website / Blogger |  | 2024-08-16
Define Opportunities Shortlist w/ market research findings |  | 2024-08-23
Contact Referring Websites / Bloggers & Review Rates |  | 2024-08-23
Select Referring Website / Blogger |  | 2024-09-09
Understand Options (Video, blog post, etc.) & Curate Content / UTM Parameters |  | 2024-10-09
Content Submission Dependent Upon Referring Website / Blogger Policy |  | TBD
📢 PAID SOCIAL 📢
Define Strategy & KPIs for Paid Social |  | 2024-08-16
Create Preview Campaigns (A/B Test Two Variants) |  | 2024-10-07
Create Promo Kickoff Campaign |  | 2024-10-08
Create Promo Ending (48 hours) Campaign |  | 2024-10-09
Create Promo Ending (24 hours) Campaign |  | 2024-10-10
Enable Preview Campaign |  | 2024-10-26
Update Preview Campaign Copy to Ongoing Copy |  | 2024-11-24
Enable Promo Ending (48 hours) Campaign |  | 48 Hours before promo end date
Enable Promo Ending (24 hours) Campaign |  | 24 Hours before promo end date
🌱 ORGANIC SOCIAL 🌱
Define Strategy & KPIs for Organic Social |  | 2024-08-16
Create Promo Countdown Posts (20) |  | 2024-10-12
Create Promo Kickoff Post(s) - quantity dependent on duration of promo |  | 2024-10-22
Create Promo Reminder Posts - quantity dependent on duration of promo |  | 2024-10-22
Schedule All Posts (countdown post scheduling: 1 - 30 days in advance, then every 5 days until 7 days in advance. 1 - 7 days in advance then daily until kickoff. 1 - At kickoff and twice daily until promo ends. |  | 2024-10-22
💥 SOCIAL INFLUENCER MARKETING 💥
Define Strategy & KPIs for Influencers |  | 2024-08-16
Define Opportunities Shortlist w/ market research findings |  | 2024-08-23
Contact Influencers & Review Rates |  | 2024-08-23
Select Influencers |  | 2024-09-09
Understand Options (Video, post copy, etc.) & Curate Content / UTM Parameters |  | 2024-10-09
Content Submission Dependent Upon Influencer Policy |  | TBD
🤑 ONGOING STRATEGY MANAGEMENT ANALYSIS 🤑
Update KPI Setting & Tracking Tab w/ Targets |  | 2024-08-16
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-11-25
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-12-02
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-12-09
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-12-16
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-12-23
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2024-12-30
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics |  | 2025-01-06

## KPI Setting & Tracking
Need a helping hand with your strategy? We got you.
KPI | TARGET | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06
📈 UNIVERSAL / SEO / CRO 📈
Users
New Users
Sessions
Engagement Rate
View Item Events
Add To Carts
Purchases (Quantity)
Revenue
🔎 GOOGLE ADS 🔎
Impressions
Clicks
CTR
Purchases (Quantity)
Cost
Revenue
ROAS
📬 EMAIL MARKETING 📬
Open Rate
CTR
Purchases (Quantity)
Revenue
💬 SMS MARKETING 💬
Open Rate
CTR
Purchases (Quantity)
Revenue
🎙 AUDIO ADVERTISING (RADIO/PODCAST) 🎙
Downloads / Listens
Completions
Promo Code Usage
Purchases (Quantity)
Revenue
🤝 PARTNER/REFERRAL MARKETING 🤝
Sessions
Users
Purchases (Quantity)
Cost
Revenue
ROAS
📢 PAID SOCIAL 📢
Impressions
Clicks
CTR
Purchases (Quantity)
Cost
Revenue
ROAS
🌱 ORGANIC SOCIAL 🌱
Followers
Impressions
Engagement Rate
Brand Mentions
Purchases (Quantity)
Revenue
💥 SOCIAL INFLUENCER MARKETING 💥
Impressions
Engagement Rate
Brand Mentions
Promo Code Usage
Purchases (Quantity)
Revenue

## Checklist - Living Document
Need a helping hand with your strategy? We got you.
CHECKLIST ITEM | DUE DATE | STATUS
🌎 UNIVERSAL 🌎
Review Previous Year Holiday Sale Performance | 2024-08-05
Research Competitor & Market Trends | 2024-08-05
Define Core Audience (Interests, Demographics & Geography) | 2024-08-05
Optimize GA4 & GTM Configurations | 2024-08-08
Define Uniform Design Elements | 2024-09-01
Create Optimized Promo Codes | 2024-08-16
Set Code Freeze Dates | 2024-09-16
Review Promotion Performance & Analyze For 2025 | 2025-03-05
📈 SEO / CRO 📈
Test & Resolve Site Speed Errors | 2024-07-28
Test & Resolve Mobile Usability Errors | 2024-07-28
Define Strategy & KPIs for Organic Performance | 2024-08-16
Publish Preview Blog | 2024-09-21
Publish Second Variant Preview Blog | 2024-10-26
Develop A/B Test Landing Page Content | 2024-09-26
Test Promo Codes | 2024-10-26
🔎 GOOGLE ADS 🔎
Define Strategy & KPIs for Google Ads | 2024-08-16
Create GA4 & Google Ads Audiences | 2024-09-21
Draft Promo Campaigns for A/B Testing (min. 2 per promo code) | 2024-09-16
Enable Campaigns w/ preview text | 2024-11-15
Update Campaigns w/ live promo text | 2024-11-24
📬 EMAIL MARKETING 📬
Define Strategy & KPIs for Email | 2024-08-16
Segment Audiences | 2024-09-06
Create Preview Email | 2024-09-09
Create Reminder Preview Email | 2024-09-09
Send Final Reminder Preview Email | 2024-09-10
Create Subscribers Only 24-hour | 2024-09-10
Create Promo Kickoff Email | 2024-09-11
Create Promo Reminder Email | 2024-09-11
Create Promo Ending (48 hours) Email | 2024-09-12
Create Promo Ending (24 hours) Email | 2024-09-12
Send Preview Email | 2024-10-26
Send Reminder Preview Email | 2024-11-11
Send Final Reminder Preview Email | 2024-11-18
Send Subscribers Only 24-hour | 2024-11-24
Send Promo Kickoff Email | 2024-11-25
Send Promo Reminder Email | 2024-11-28
Send Reminder emails every 2 days until 48 hours before promo end | N/A
Send Promo Ending (48 hours) Email | 48 Hours before promo end date
Send Promo Ending (24 hours) Email | 24 Hours before promo end date
💬 SMS MARKETING 💬
Define Strategy & KPIs for SMS | 2024-08-16
Segment Audiences | 2024-09-06
Create Preview SMS | 2024-09-09
Create Reminder Preview SMS | 2024-09-09
Send Final Reminder Preview SMS | 2024-09-10
Create Subscribers Only 24-hour | 2024-09-10
Create Promo Kickoff SMS | 2024-09-11
Create Promo Reminder SMS | 2024-09-11
Create Promo Ending (48 hours) SMS | 2024-09-12
Create Promo Ending (24 hours) SMS | 2024-09-12
Send Preview SMS | 2024-10-26
Send Reminder Preview SMS | 2024-11-11
Send Final Reminder Preview SMS | 2024-11-18
Send Subscribers Only 24-hour | 2024-11-24
Send Promo Kickoff SMS | 2024-11-25
Send Promo Reminder SMS | 2024-11-28
Send Reminder SMSs every 2 days until 48 hours before promo end | N/A
Send Promo Ending (48 hours) SMS | 48 Hours before promo end date
Send Promo Ending (24 hours) SMS | 24 Hours before promo end date
🎙 AUDIO ADVERTISING (RADIO/PODCAST) 🎙
Define Strategy & KPIs for Radio/Podcast | 2024-08-16
Define Opportunities Shortlist w/ market research findings | 2024-08-23
Contact Podcasts/Stations & Review Rates | 2024-08-23
Select Podcast(s) / Station(s) | 2024-09-09
Understand Options (Host-Read, etc.) & Curate Content / UTM Parameters | 2024-10-09
Content Submission Dependent Upon Podcast/Radio Policy | TBD
🤝 PARTNER/REFERRAL MARKETING 🤝
Define Strategy & KPIs for Referring Website / Blogger | 2024-08-16
Define Opportunities Shortlist w/ market research findings | 2024-08-23
Contact Referring Websites / Bloggers & Review Rates | 2024-08-23
Select Referring Website / Blogger | 2024-09-09
Understand Options (Video, blog post, etc.) & Curate Content / UTM Parameters | 2024-10-09
Content Submission Dependent Upon Referring Website / Blogger Policy | TBD
📢 PAID SOCIAL 📢
Define Strategy & KPIs for Paid Social | 2024-08-16
Create Preview Campaigns (A/B Test Two Variants) | 2024-10-07
Create Promo Kickoff Campaign | 2024-10-08
Create Promo Ending (48 hours) Campaign | 2024-10-09
Create Promo Ending (24 hours) Campaign | 2024-10-10
Enable Preview Campaign | 2024-10-26
Update Preview Campaign Copy to Ongoing Copy | 2024-11-24
Enable Promo Ending (48 hours) Campaign | 48 Hours before promo end date
Enable Promo Ending (24 hours) Campaign | 24 Hours before promo end date
🌱 ORGANIC SOCIAL 🌱
Define Strategy & KPIs for Organic Social | 2024-08-16
Create Promo Countdown Posts (20) | 2024-10-12
Create Promo Kickoff Post(s) - quantity dependent on duration of promo | 2024-10-22
Create Promo Reminder Posts - quantity dependent on duration of promo | 2024-10-22
Schedule All Posts (countdown post scheduling: 1 - 30 days in advance, then every 5 days until 7 days in advance. 1 - 7 days in advance then daily until kickoff. 1 - At kickoff and twice daily until promo ends. | 2024-10-22
💥 SOCIAL INFLUENCER MARKETING 💥
Define Strategy & KPIs for Influencers | 2024-08-16
Define Opportunities Shortlist w/ market research findings | 2024-08-23
Contact Influencers & Review Rates | 2024-08-23
Select Influencers | 2024-09-09
Understand Options (Video, post copy, etc.) & Curate Content / UTM Parameters | 2024-10-09
Content Submission Dependent Upon Influencer Policy | TBD
🤑 ONGOING STRATEGY MANAGEMENT ANALYSIS 🤑
Update KPI Setting & Tracking Tab w/ Targets | 2024-08-16
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-11-25
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-12-02
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-12-09
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-12-16
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-12-23
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2024-12-30
Update KPI Setting & Tracking Tab w/ previous 7 days' performance metrics | 2025-01-06

## Budget
Need a helping hand with your strategy? We got you.
EXPENSE | COST | MULTIPLIER | TOTAL COST
Influencer 1
Influencer 2
Podcast 1
Social Ads (Meta)
Social Ads (Tiktok)
Social Ads (X)
Google Ads
TOTAL COST:
BUDGET:

## Promo Codes
Need a helping hand with your strategy? We got you.
Code | Enable Date | End Date | Summary | Tested
Subscribers Only
Podcast 1 Code
A/B Test Variant 1
A/B Test Variant 2
Influencer 1 Code
Influencer 2 Code

## Design Assets
Need a helping hand with your strategy? We got you.
ITEM | DIMENSIONS | SUMMARY
Home Page Banner | TBD | Create one per promo code - Dimensions dependent on template and platform
Facebook Profile Banner | TBD | Create one per promo code - Dimensions dependent on template and platform
Google Ads Campaign 1:1 | 1200x1200 | Create one per product and a minimum of 5 for general advertising - per A/B variant
Google Ads Campaign 1.91:1 | 1200x628 | Create one per product and a minimum of 5 for general advertising - per A/B variant
Email Banner - Preview | TBD | Dimensions dependent on template and platform
Email Banner - Preview Reminder | TBD | Dimensions dependent on template and platform
Email Banner - Final Reminder Preview | TBD | Dimensions dependent on template and platform
Email Banner - Subscribers Only | TBD | Dimensions dependent on template and platform
Email Banner - Promo Kickoff | TBD | Dimensions dependent on template and platform
Email Banner - Promo Reminder | TBD | Dimensions dependent on template and platform
Email Banner - Promo Ending (48 hours) | TBD | Dimensions dependent on template and platform
Email Banner - Promo Ending (24 hours) | TBD | Dimensions dependent on template and platform
Influencer Assets (TBD) | TBD | Dimensions dependent on template and platform
Refferal Site Assets (TBD) | TBD | Dimensions dependent on template and platform
Meta Ads 1:1 | 1080x1080 | Create a minimum of 5 for general advertising - per A/B variant
Meta Ads 16:9 | 1080 x 566 | Create a minimum of 5 for general advertising - per A/B variant
Meta Carousel Ads 1:1 | 1080x1080 | Create one per product - per A/B variant
Additional Social Media Ads
Video Ads - Tiktok